## Plan
Things we will do | Prerequisite | Action needed | Time length
API Integration | Needed before we start • API access and credentials from the source system owners • API documentation and list of endpoints / data fields • Sandbox or test environment available | Steps 1. Get API specs and access from the client IT team 2. Build and test the integration with the platform 3. Validate the API data against sample data | TBD (to be confirmed once API access is granted)
Other outlier checks and other requirements Examples of what we need to cover: • Target group: quality vs logistics vs higher management • Products: single product vs multiple products • Transport: single-leg vs multi-leg • Direction: inbound vs outbound • Focus level: supplier, product, lane or other | Data and samples needed from • Quality • Logistics • Higher management For each scope item on the left • Sample data for single / multiple products, single / multi-leg, inbound / outbound • Sample data at supplier, product and lane level Rules needed • What to check and what counts as an outlier • What to do when an outlier is found | Scenario A: Proper rules received 1. Request data and samples from each target group 2. Review the samples with them and confirm the rules 3. Build the outlier checks directly from the rules | Nov 15
|  | Scenario B: Explore and identify 1. Request data and samples from each target group 2. Explore the data and identify outliers / patterns ourselves 3. Agree the rules with them, then build the checks | Nov 25