## Plan
Things we will do | Prerequisite | Action needed | Time length
API Integration | Needed before we start • API access and credentials from the source system owners • API documentation and list of endpoints / data fields • Sandbox or test environment available | Steps 1. Get API specs and access from the client IT team 2. Build and test the integration with the platform 3. Validate the API data against sample data | TBD (to be confirmed once API access is granted)
Other outlier checks and other requirements Examples of what we need to cover: • Target group: quality vs logistics vs higher management • Products: single product vs multiple products • Transport: single-leg vs multi-leg • Direction: inbound vs outbound • Focus level: supplier, product, lane or other | Data and samples needed from • Quality • Logistics • Higher management Sample data for each case • One sample for each example case on the left (target group, single / multiple products, single / multi-leg, inbound / outbound, supplier / product / lane) • The sample should show how that case is handled today How it is processed today • Walk through how the PMs process each case, step by step • All the rules the PMs use: what to check, what counts as an outlier, and what to do when one is found • Any tribal knowledge: unwritten rules, experience-based judgement and exceptions that are not documented | Scenario A: Proper rules received 1. Request data and samples from each target group 2. Review the samples with them and confirm the rules 3. Build the outlier checks directly from the rules | Nov 15
|  | Scenario B: Explore and identify 1. Request data and samples from each target group 2. Explore the data and identify outliers / patterns ourselves 3. Agree the rules with them, then build the checks | Nov 25