## Plan
Things we will do | Prerequisite | Action needed | Time length
API Integration and Chatbot Integration | We got these • API access and credentials from the source system owners • API documentation and list of endpoints / data fields • Sandbox or test environment, if available, to test the write back to SWP | Steps 1. Got API specs and access from the client IT team 2. Build and test the integration with the platform 3. Validate the API data against sample data 4. Integrate the chatbot with the platform and the APIs 5. Test the chatbot end to end | TBD (to be confirmed once API access is granted)
Other outlier checks and other requirements Examples of what we need to cover: • Target group: quality vs logistics vs higher management • Products: single product vs multiple products • Transport: single-leg vs multi-leg • Direction: inbound vs outbound • Focus level: supplier, product, lane or other | Data and samples needed from • Quality • Logistics • Higher management Sample data for each case • One sample for each example case on the left (target group, single / multiple products, single / multi-leg, inbound / outbound, supplier / product / lane) • The sample should show how that case is handled today How it is processed today • Walk through how the PMs process each case, step by step • All the rules the PMs use: what to check, what counts as an outlier, and what to do when one is found • Any tribal knowledge: unwritten rules, experience-based judgement and exceptions that are not documented | Scenario A: Proper rules received 1. Request data and samples from each target group for every case (outlier checks, data changes, multi-hop data and other requirements) 2. Review the samples with them and confirm the rules for each case 3. Build the checks and logic for each case directly from the rules | Nov 15
|  | Scenario B: Explore and identify 1. Request data and samples from each target group for every case (outlier checks, data changes, multi-hop data and other requirements) 2. Explore the data and identify the outliers, data changes and multi-hop patterns ourselves 3. Agree the rules for each case with them, then build the checks and logic | Nov 25